## Read me
How to use this workbook
Two tables: G702 Summary (the certificate and payment due) and G703 Schedule (one row per schedule of values line).
Type only into the shaded cells. Everything else is a formula. It opens in Excel, Apple Numbers, Google Sheets and LibreOffice, with no macros.
G703 Schedule: type A to F for each line. G, H, % and the totals row compute.
G702 Summary: type the project details, Lines 1 and 2, the retainage rate and Line 7. Line 4, retainage and the payment due compute.
Retainage that varies by line: type the total over Line 5.
More lines: insert rows above the Column totals row, then copy a full row down into them so the formulas come along.
Next month, in a copy of this file:
1. G703 Schedule: copy the column Next month's D and paste it over column D as values. Excel: Paste Special, Values. Numbers on Mac: Edit, Paste Formula Results. Google Sheets: Paste special, Values only.
2. Clear column E, then type this month's work.
3. Update column F to the material stored now. Material installed since last month moves into E.
4. G702 Summary: type last month's Line 6 into Line 7, and change the application no. and period.
This is not the official AIA form. It follows the same columns, lines and arithmetic.
Provided as is. Check the figures. Not legal or accounting advice.
Next month, upload this file at payappcheck.com/tools/g703-checker and your figures carry forward: Column D, Line 7 and the application number up one. Or send the finished pay app to your GC from there, with a link that shows the figures tie. A free account covers both.

## G702 Summary
Line | Amount
Project
From contractor
To owner
Application no.
Period to
1. Original contract sum
2. Net change by change orders
3. Contract sum to date (1 + 2) | 0
4. Total completed and stored to date (G703 column G total) | 0
Retainage rate, percent (for example 10)
5a. Retainage on completed work (rate × G703 D + E) | 0
5b. Retainage on stored material (rate × G703 F) | 0
5. Total retainage (5a + 5b) | 0
6. Total earned less retainage (4 − 5) | 0
7. Less previous certificates (last month's Line 6)
8. Current payment due (6 − 7) | 0
9. Balance to finish, including retainage (3 − 6) | 0
Check: Line 3 equals G703 column C total | Ties
Free template from payappcheck.com

## G703 Schedule
A · Item No. | B · Description of Work | C · Scheduled Value | D · From Previous Application (last month's D + E) | E · Work Completed This Period | F · Materials Presently Stored (not in D or E) | G · Total Completed and Stored (D + E + F) | H · Balance to Finish (C − G) | % Complete (G ÷ C) | Next month's D (D + E)
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
[6 empty] | 0 | 0 | 0% | 0
| Column totals | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
Free template from payappcheck.com